## README
Profile Control Feasibility Checklist
Please Read this Page before Using the Profile Control Feasibility Checklist!
Notes Specific to this Checklist:
Channel Profile Control is often used as fish passage remedy in itself (e.g. regrading a stream below an existing pipeline, road or syphon crossing a stream OR as a component of another project (e.g. dam removal , road crossing retrofit) to solve a discontinuity in the vertical longitudinal profile of a channel.
This Version ( Version 1) contains only the basic feasibility checklist with a minimum of references and details. Expanded revisions are intended.
This checklist is to be used as an aid when taking a first in-depth look at a potential profile control project to determine A) if the project is feasible and B) what are the major issues and participants that need to be considered for implementation of the project. Unlike some of the other checklists, it is NOT a comprehensive design guide.
About the Checklists:
The Education Committee of the BioEngineering Section (BES) of the American Fisheries Society (AFS) is providing a series of checklists for implementing fish passage and habitat projects as a service to our community of practice, especially newer practitioners and on the ground project managers. These checklists are provided with the intent of fostering more successful projects with fewer missteps and less backtracking. The following are a few notes to help make use of these checklists:
The checklists are targeted to common, small and moderate scale civil works projects being performed to remedy fish passage problems or for habitat improvement. They are not meant to address large and complex projects, nor will they perfectly serve all cases.
The checklists are to be used as prompts to consider what to enact or provide for a particular project type. The intent is not that each item should be performed, but the practitioner should consider each item to determine if it is required or beneficial to a successful project. It is unlikely that any project will enact ALL the items on a checklist, and conversely these checklists should be considered a starting point, with additional steps that may be necessary for a site or geographic area.
Individual checklists have been assembled for Aquatic Organism Passage, Fishways, Eel Passes, Dam Removals, Stream Profile Control, and Small Screens. Additional check lists may be included over time. Checklists were developed by experts in each type of project, based on the best available guidance rooted in existing science, engineering and training resources.
These checklists are not being endorsed by AFS or BES. There are other project checklists available from other authorities on these topics. Some can be found within training documents found at our other product, the Fish Passage Training Portal, available at the project homepage linked below. If you think the below collection of checklists would benefit from another category of project or have other feedback, please write to: rweiter@eaest.com
Glossary: | A glossary of terms related to fish passage and stream restoration implementation has been compiled from various sources into a single file for ease of reference and can be downloaded from the project home page. | Project Home Page:
https://units.fisheries.org/fishpassagejointcommittee/fishpassagetrainingportal/
Fish Passage Training Portal: | A compendium of fish passage-related training resources and links to electronic data developed to provide a centralized and vetted list of resources to new practicitioners or those looking to expand their knowledge.

## Profile Control Feasibility
Profile Control Feasibility Checklist for Project Proponents
Adapted from Laura Wildman
Profile Control (e.g. rock weirs, roughened channel, boulder garden) is often a component of an fish passage project (such as a road crossing ,small dam removal or gravity diversion)
|  |  | Question | Yes/No | Comments (from Project Proponents)
Ownership |  |  | Are the streambank owners in opposition to profile control, regardless of cost and the outcome of a Feasibility Analysis? |  |  | FALSE | FALSE
Access |  |  | Are there any insurmountable issues with getting permissions to access the reprofiling reach of channel? |  |  | TRUE | FALSE
Infrastructure/utility impacts
| Bridges1 |  | Is there a bridge at the intended channel regrade or upstream, that would be undermined by the new profile control (i.e. the foundations of the abutments or any in-channel piers are shallow and potentially resting on impounded sediment)?
| Culverts2 |  | Is there a culvert upstream, that might be undermined by the new profile control?
| Buildings |  | Is there a foundation of a building near the channel that could be undermined by the new profile control?
| Roadways/Railroad |  | Is there a paralleling roadway or railroad embankment that could be undermined by the new profile control?
| Retaining walls |  | Is there a retaining wall or slope protection that could be undermined by the new profile control?
| Subsurface utility pipes/lines3 |  | Are there any subsurface utility pipes or lines that could become exposed or undermined by the new profile control?
| Overhead utilities |  | Are there any overhead wires that are low enough to create a problem for construction equipment during the profile control construction or that might make accessing the site impossible?
| Wells |  | Are there water supply or residential wells near the project that could be impacted as a result of the profile control project ?
| USGS Gage |  | Is there a USGS Gage that could be impacted by the profile control ?
Geomorphic equilibrium4 |  |  | Is there any signs of geomorphic instabilities in the channel below the treatment site (i.e. is their a headcut at or near the downstream end? Is there an nearby landslide site?)
Longitudinal Channel Survey5 |  |  | The length of channel upstream and downstream needed for a pre-project longitudial survey should be determined. Any access issues within this length of channel?
Historic/archeological6 |  |  | Are there any known historic or archeological concerns that may preclude the profile control project?
Environmental concerns & benefits |  |  | Are there highly valued man-made wetlands that will be eliminated by the new profile control (i.e. high value wetlands that were created due to channel's current profile that would be lost)?
Sensitive or invasive species7 |  |  | Is there a Rare, Threatened or Endangered Species within the impoundment or a wetland associated with project area, that cannot be suitably protected? (Note: if there is a RTE species downstream typically suitable sediment and flow management can be incorporated into the project design to protect those RTE species)
Cost & funding availability8 |  |  | Is there no funding available for the profile control project? (see resources described below)
If the answers to the first and/or second questions are YES, then dam removal is not feasible.
If the answer to these two questions is NO than it is highly likely that removing the profile control project is feasible and likely would result in an overall improved ecological condition for the river system.
If one or more of the answers to the remaining questions was YES or UNKNOWN, then additional work is needed to ensure that the profile control project is feasible, and can be completed with no increased human risks and minimum impacts to the environment and infrastructure/utilities.
DESCRIPTION & METHODS
1 |  | Bridges | If there are bridges over or upstream of the project site, within the extent of an existing impoundment under high flows, it is very helpful to gather bridge engineering design plans from the municipality, state DOT or Federal Highway Administration if they exist. These plans should show the extend of the abutment and pier foundations and describe if the footings are founded on bedrock, piers, or are spread footings potentially on impounded sediment. As built plans are always preferred since the footings of the bridge may have been modified during constructions to adapt to conditions found in the field.
2 |  | Culverts | If there are culverts upstream of or within the extent of the project reach, they could become subject to scour or exposure and therefore be either undermined or transition into a drop culvert outlet (potentially adding discontinuity to tributary drainage), this needs to be checked Investigation of the culvert in relation to the anticipated channel invert, water depth drops and sediment transport will be important.
3 |  | Subsurface Utilities | The municipality and or state should be contacted to help determine if there are subsurface utilities near the project site or within the area of impact. It is especially critical to identify subsurface utilities that cross the channel bed or impoundment for these can be undermined or exposed post project. However utilities paralleling the river or impoundment may also become an issue and should be identified. Most states have a services that can help identify these subsurface utilities (i.e. Ohio811; CT: Call Before You Dig; PA One Call)
4 |  | Geomorphic equilibrium | If the downstream channel is highly entrenched that could be a sign that a headcut has extended to the base of the project site. Altering the vertical profile without adequate stabilization could therefore propagate that headcut farther upstream and cut into what was the underlying streambed material prior to the placement of the present discontinuity (e.g. road, syphon crossing) being addressed. This can lead to an "unraveling" and entrenchment of the upstream system and the profile control design would need to determine the best method to limit or mitigate this potential impact prior to proceeding with profile control of the reach addressed by the project.
5 |  | Longitudinal Survey | Both for determination of overall channel stability and calculation of material sizes, determination a pre-project and post-project vertical profile is central to this project type. This requires a pre-project longitudinal survey. Underestimating the length of this survey (usually proportionate to the overall change in grade being addressed) is the most common design error in these project types. Access to this entire reach is typically not needed frequently or for construction - pedestrian access is usually sufficient.
6 |  | Historic/archeological | Any structure over 50 years in age has the potential to be historic, and archeological sites could have been submerged if there is an impoundment caused by the vertical discontinuity being addressed, thereby protecting them from looting. It is therefore critical to contact the State Historic Preservation Office (SHPO) to ask if there are resources of historic value or if there are any archeological concerns if the channel were to be reprofiled.
7 |  | Sensitive or invasive species | Check the state databases to determine if there are any rare, threatened or endangered species upstream or downstream of the dam. For the upstream reach, extend your search just above the extent of potential impact. For the downstream reach, extend your search to the confluence with the next major river or tributary.
8 |  | Cost & funding availability | There are numerous funding sources that can help reduce the cost of a profile control for project proponents. Some of these resources can be found at: https://www.americanrivers.org/river-restoration-funding-sources/