## READ ME
Reference
Paul D. Powers and Matt Helstab and Sue L. Niezgoda A process-based approach to restoring depositional river valleys to Stage 0, an anastomosing channel network, River Research and Applications} 2019-01-20 ¦ Journal article DOI: 10.1002/rra.3378
Brian Cluer, Colin Thorne, A stream elevolution model intergrating habitat and ecosystem benefits, River Research and Applications} 30: 135-154, 2013-01-10 ¦ Journal article, DOI: 10.1002/rra.2631
THIS SPREADSHEET CHECKLIST WAS DEVELOPED TO SUPPORT PROCESS-BASED RESTORATION TO STAGE ZERO CONDITION IN DEPOSITIONAL ENVIRONMENTS. THE CHECKLIST WAS DEVELOPED BY PAUL POWERS, MATT HELSTAB, BRIAN CLUER AND JOHAN HOGERVORST AND IS A WORK IN PROGRESS. THE CURRENT CHECKLIST DESCRIBES DETAILED ASPECTS OF ASSESSMENT (FROM WATERSHED SCALE TO PROJECT-LEVEL SCALE), DESIGN, IMPLEMENTATION AND MONITORING, IDENTIFYING KEY DECISION POINTS ALONG THE WAY TO DETERMINE THE PROPER IMPLEMENTATION APPROACH. DIAGRAMS AND DISCUSSION WERE ADDED BY BRIAN CLUER TO INFORM THE DECISIONS TO BE MADE. A MORE GENERALIZED FLOW CHART OF THE PROCESS IS YET TO BE DEVELOPED - AN EXAMPLE IS INCLUDED IN THE THIRD AND FINAL TAB OF THIS SPREADSHEET. ADDITIONAL REFERENCES ON THE STREAM EVOLUTION MODEL AND VALLEY RESET TO STAGE 0 CONDITION ARE INCLUDED BELOW. ANY QUESTIONS CONCERNING THE CHECKLIST SHOULD BE DIRECTED TO MATT.HELSTAB@USDA.GOV.

## Stage 0 Workflow
PROJECT SETUP | PROJECT SETUP | Type of Analysis | Notes
| Establish a project tracking document | Narrative | Promote best practices. We often don't keep good notes as we build projects.
| Identify project geography | GIS Mappaing and Analysis | Where are we?
| Identify project stakeholders | Discussion | Who is here?
| Identify broad project goals and objectives | Discussion | Why here, why now?
| Setup ArcGIS Pro project map and gather supporting spatial data | GIS Workflow | Example list of supporting data (3DEP, NHD, WBD, GEOLOGY, SOILS, OWNERSHIP, DOGAMI, ETC.)
WATERSHED ASSESSMENT | WATERSHED ASSESSMENT (WHOLE WATERSHED SCALE)
| Evaluate local geologic processes (bedrock, structure, faults/slips/slides, age of flows etc.) | INFORMATION COLLECTION AND INTERPRETATION
Evaluate local climate (precipitation type, amount, timing, etc.)
Evaluate local vegetation patterns (upland, riparian, etc.)
Evaluate relative sediment supply (high/low yield, size)
Evaluate local ecological processes
Evaluate species presense and distribution (native vs non-native, ESA, etc.)
Evaluate local land-use patterns and practices (ownership, management, recreation, etc.)
Consider social values for the project area (cultural, economic, etc.)
| Isolate valley floor process space from hillslope process space | GIS WORKFLOW
Build NHD-IDW-REM
Build Valley Bottom Polygon (VBP) from NHD-IDW-REM
Build valley bottom elevation bands/contours
Build Valley Centerline (VCL)
Build Valley Centerline Stations (VCL-Stations)
Build Valley Centerline Cross-sections (VCL-XSEC)
| Identify distinct valley segments and geomorphic controls | GIS WORKFLOW
Evaluate valley slope/curvature from VCL-Stations
Evaluate valley width/confinement from VCL-XSEC clipped to VBP
Build discrete VBPs between geomorphic controls
| Reevaluate watershed specific context with VBPs | DISCUSSION AND INTERPRETATION
| Evaluate Distribution of Stream Evolution Model (SEM) Stages Across Watershed | DECISION POINT
| Summarize findings and produce overview maps | DISCUSSION, DOCUMENTATION, & MAPPING
Identify project goals and objectives with partners
RIVER/VALLEY ASSESSMENT | RIVER/VALLEY ASSESSMENT (DISCRETE VALLEY SCALE)
| Evaluate local geomorphology | GIS WORKFLOW
Evaluate local hydrology-Trends, potential near future, temperature
Evaluate depth to groundwater
Evaluate condition of geomorphic controls and transitions
Evaluate local riparian vegetation
Evaluate local ecological processes
Evaluate species presense
Evaluate local land-use patterns and practices (ownership, management, recreation, etc.)
Evaluate soil, alluvial stratigraphy-depths, distribution-Buried Valleys
Identify anthropogenic valley floor features-Buried Valleys
Consider social values for the project area (cultural, economic, etc.)
| Build GGL-REM, discrete Relative Elevation Models (REM) from Geomorphic Grade Line (GGL) | GIS WORKFLOW
Build discrete Valley Centerline (VCL) between geomorphic controls
Build Valley Centerline Stations (VCL-Stations)
Build Valley Centerline Cross-sections (VCL-XSEC)
Evaluate valley slope/curvature from VCL-Stations
Fit polynomial regression (least squares) to VCL-Station elevations
Append modeled VCL-Station elevations to VCL-XSEC
Build GGL-Raster (VCL-XSEC to Raster)
Build GGL-REM (LiDAR minus GGL-Raster)
| Build Existing Surface Flow Models (ESFM) @ Baseflow, Q2, Q10, and Q100 | HEC-RAS WORKFLOW
Evaluate Hydrograph from gauge where possible for a given water year
Describe Velocity, Depth, Inundation Area and Duration
Describe habitat suitability by species and life-stage
| Build Filled to Target Flow Models (F2TFM) @ Baseflow, Q2, Q10, and Q100 | HEC-RAS WORKFLOW
Evaluate Hydrograph from gauge where possible for a given water year
Describe Velocity, Depth, Inundation Area and Duration
Describe habitat suitability by species and life-stage
PROJECT ASSESSMENT | Evaluate Valley Bottom Restoration Potential Versus Current Condition (SEM) | DECISION POINT
Evaluate restoration timeline goals (Process-led vs Process-reset)
| Summarize findings and produce overview maps | DISCUSSION, DOCUMENTATION, & MAPPING
Refine project goals and objectives with partners
Evaluate finding in the field with project partners
| Gather site specific context (disturbance, geomorphology, soils, ecology, etc.) | FIELD DATA COLLECTION
Map fluvial process-space (high, low, and target surfaces, relative to GGL-REM target)
Identify non-fluvial surfaces on the valley floor (wetlands, fans, slides, etc.)
Identify evidence of distrubed surfaces (berms, roads, landings, logging, grazing, etc.)
Evaluate substrate types and distribution
Map vegetation, species and age by surface layer
| Define the potential pre-degradation condition | DISCUSSION, DOCUMENTATION, & MAPPING
Define degree of degradation, anthropogenic legacy impacts
Georeference Historic Aerial Photos and evaluate channel changes
Assess Infrastructure and potential needs for improvement (roads, bridges, trails, etc.)
| Summarize findings and produce overview maps | DISCUSSION, DOCUMENTATION, & MAPPING
Refine project goals and objectives with partners
PROJECT DESIGN | Determine Restoration Approach (SEM Stage & Process-Led vs Process-Reset) | DECISION POINT
Valley Bottom Restoration Design (Process-Reset to Stage 0/8)
| Build field validated GGL-REM | GIS WORKFLOW
Develop Fill Polygons (area, volume, source)
Develop Cut Polygons (area, volume)
Identify unique project areas (staging areas, avoidence areas, habitat units, etc.)
Develop Roughness Plan (classify and quantify by type and size class, identify sources)
Develop Flow Management Plan (FMP) (dewatering, fish salvage, turbidity mangement, etc.)
Determine equipment access routes
| Build Design Surface Flow Model (DSFM) @ Baseflow, Q2, Q10, and Q100 | HEC-RAS WORKFLOW
Evaluate Hydrograph from gauge where possible for a given water year
Describe Velocity, Depth, and Inundation
Describe habitat suitability by species and life-stage
| Produce overview maps and PowerPoint of findings | DISCUSSION, DOCUMENTATION, & MAPPING
Refine project goals and objectives with partners
| Develop re-vegetation plan (species, locations, spacing, etc.) | DISCUSSION, DOCUMENTATION, & MAPPING
Develop design logistics and construction needs and sequencing of project elements
Develop Design Packet for Permits
PROJECT IMPLEMENTATION | Implementation and Inspection (Process-Reset)
Public notification and potential area closures
Construction staking (Elevation Hubs, Avoidance Areas, Retention Pools, etc)
Clearing (Access Routes and Cut Surfaces)
Harvest, deliver, and stockpile large wood
Dewatering (construct flow diversion / bypass channel(s), fish salvage, turbidity management, etc.)
Excavate material from cut source areas
Place fill in Incised Channels
Place, bury, and construct large wood structures
Rewater completed surfaces and remove dewatering facilities
Revegetated disturbed areas
Repair permanent access routes, Decommission Staging/stockpile areas and temp access routes
MONITORING | Post-Project Monitoring and Assessment
Establish a monitoring plan to track goals and objectives of the project
Analyze and report on the results of monitoring data
Document lessons learned throughout the project
Share outcomes (presentations, site visits, story maps, publish, etc.)