## READ ME
Reference
Paul D. Powers and Matt Helstab and Sue L. Niezgoda A process-based approach to restoring depositional river valleys to Stage 0, an anastomosing channel network, River Research and Applications} 2019-01-20 ¦ Journal article DOI: 10.1002/rra.3378
Brian Cluer, Colin Thorne, A stream elevolution model intergrating habitat and ecosystem benefits, River Research and Applications} 30: 135-154, 2013-01-10 ¦ Journal article, DOI: 10.1002/rra.2631
THIS SPREADSHEET CHECKLIST WAS DEVELOPED TO SUPPORT PROCESS-BASED RESTORATION TO STAGE ZERO CONDITION IN DEPOSITIONAL ENVIRONMENTS. THE CHECKLIST WAS DEVELOPED BY PAUL POWERS, MATT HELSTAB, BRIAN CLUER AND JOHAN HOGERVORST AND IS A WORK IN PROGRESS. THE CURRENT CHECKLIST DESCRIBES DETAILED ASPECTS OF ASSESSMENT (FROM WATERSHED SCALE TO PROJECT-LEVEL SCALE), DESIGN, IMPLEMENTATION AND MONITORING, IDENTIFYING KEY DECISION POINTS ALONG THE WAY TO DETERMINE THE PROPER IMPLEMENTATION APPROACH. DIAGRAMS AND DISCUSSION WERE ADDED BY BRIAN CLUER TO INFORM THE DECISIONS TO BE MADE. A MORE GENERALIZED FLOW CHART OF THE PROCESS IS YET TO BE DEVELOPED - AN EXAMPLE IS INCLUDED IN THE THIRD AND FINAL TAB OF THIS SPREADSHEET. ADDITIONAL REFERENCES ON THE STREAM EVOLUTION MODEL AND VALLEY RESET TO STAGE 0 CONDITION ARE INCLUDED BELOW. ANY QUESTIONS CONCERNING THE CHECKLIST SHOULD BE DIRECTED TO MATT.HELSTAB@USDA.GOV.

## Stage 0 Workflow
PROJECT SETUP | PROJECT SETUP | Type of Analysis | Notes
| Establish a project tracking document | Narrative | Promote best practices. We often don't keep good notes as we build projects.
| Identify project geography | GIS Mappaing and Analysis | Where are we?
| Identify project stakeholders | Discussion | Who is here?
| Identify broad project goals and objectives | Discussion | Why here, why now?
| Setup ArcGIS Pro project map and gather supporting spatial data | GIS Workflow | Example list of supporting data (3DEP, NHD, WBD, GEOLOGY, SOILS, OWNERSHIP, DOGAMI, ETC.)
WATERSHED ASSESSMENT | WATERSHED ASSESSMENT (WHOLE WATERSHED SCALE)
| Evaluate local geologic processes (bedrock, structure, faults/slips/slides, age of flows etc.) | INFORMATION COLLECTION AND INTERPRETATION
Evaluate local climate (precipitation type, amount, timing, etc.)
Evaluate local vegetation patterns (upland, riparian, etc.)
Evaluate relative sediment supply (high/low yield, size)
Evaluate local ecological processes
Evaluate species presense and distribution (native vs non-native, ESA, etc.)
Evaluate local land-use patterns and practices (ownership, management, recreation, etc.)
Consider social values for the project area (cultural, economic, etc.)
| Isolate valley floor process space from hillslope process space | GIS WORKFLOW
Build NHD-IDW-REM
Build Valley Bottom Polygon (VBP) from NHD-IDW-REM
Build valley bottom elevation bands/contours
Build Valley Centerline (VCL)
Build Valley Centerline Stations (VCL-Stations)
Build Valley Centerline Cross-sections (VCL-XSEC)
| Identify distinct valley segments and geomorphic controls | GIS WORKFLOW
Evaluate valley slope/curvature from VCL-Stations
Evaluate valley width/confinement from VCL-XSEC clipped to VBP
Build discrete VBPs between geomorphic controls
| Reevaluate watershed specific context with VBPs | DISCUSSION AND INTERPRETATION
| Evaluate Distribution of Stream Evolution Model (SEM) Stages Across Watershed | DECISION POINT
| Summarize findings and produce overview maps | DISCUSSION, DOCUMENTATION, & MAPPING
Identify project goals and objectives with partners
RIVER/VALLEY ASSESSMENT | RIVER/VALLEY ASSESSMENT (DISCRETE VALLEY SCALE)
| Evaluate local geomorphology | GIS WORKFLOW
Evaluate local hydrology-Trends, potential near future, temperature
Evaluate depth to groundwater
Evaluate condition of geomorphic controls and transitions
Evaluate local riparian vegetation
Evaluate local ecological processes
Evaluate species presense
Evaluate local land-use patterns and practices (ownership, management, recreation, etc.)
Evaluate soil, alluvial stratigraphy-depths, distribution-Buried Valleys
Identify anthropogenic valley floor features-Buried Valleys
Consider social values for the project area (cultural, economic, etc.)
| Build GGL-REM, discrete Relative Elevation Models (REM) from Geomorphic Grade Line (GGL) | GIS WORKFLOW
Build discrete Valley Centerline (VCL) between geomorphic controls
Build Valley Centerline Stations (VCL-Stations)
Build Valley Centerline Cross-sections (VCL-XSEC)
Evaluate valley slope/curvature from VCL-Stations
Fit polynomial regression (least squares) to VCL-Station elevations
Append modeled VCL-Station elevations to VCL-XSEC
Build GGL-Raster (VCL-XSEC to Raster)
Build GGL-REM (LiDAR minus GGL-Raster)
| Build Existing Surface Flow Models (ESFM) @ Baseflow, Q2, Q10, and Q100 | HEC-RAS WORKFLOW
Evaluate Hydrograph from gauge where possible for a given water year
Describe Velocity, Depth, Inundation Area and Duration
Describe habitat suitability by species and life-stage
| Build Filled to Target Flow Models (F2TFM) @ Baseflow, Q2, Q10, and Q100 | HEC-RAS WORKFLOW
Evaluate Hydrograph from gauge where possible for a given water year
Describe Velocity, Depth, Inundation Area and Duration
Describe habitat suitability by species and life-stage
PROJECT ASSESSMENT | Evaluate Valley Bottom Restoration Potential Versus Current Condition (SEM) | DECISION POINT
Evaluate restoration timeline goals (Process-led vs Process-reset)
| Summarize findings and produce overview maps | DISCUSSION, DOCUMENTATION, & MAPPING
Refine project goals and objectives with partners
Evaluate finding in the field with project partners
| Gather site specific context (disturbance, geomorphology, soils, ecology, etc.) | FIELD DATA COLLECTION
Map fluvial process-space (high, low, and target surfaces, relative to GGL-REM target)
Identify non-fluvial surfaces on the valley floor (wetlands, fans, slides, etc.)
Identify evidence of distrubed surfaces (berms, roads, landings, logging, grazing, etc.)
Evaluate substrate types and distribution
Map vegetation, species and age by surface layer
| Define the potential pre-degradation condition | DISCUSSION, DOCUMENTATION, & MAPPING
Define degree of degradation, anthropogenic legacy impacts
Georeference Historic Aerial Photos and evaluate channel changes
Assess Infrastructure and potential needs for improvement (roads, bridges, trails, etc.)
| Summarize findings and produce overview maps | DISCUSSION, DOCUMENTATION, & MAPPING
Refine project goals and objectives with partners
PROJECT DESIGN | Determine Restoration Approach (SEM Stage & Process-Led vs Process-Reset) | DECISION POINT
Valley Bottom Restoration Design (Process-Reset to Stage 0/8)
| Build field validated GGL-REM | GIS WORKFLOW
Develop Fill Polygons (area, volume, source)
Develop Cut Polygons (area, volume)
Identify unique project areas (staging areas, avoidence areas, habitat units, etc.)
Develop Roughness Plan (classify and quantify by type and size class, identify sources)
Develop Flow Management Plan (FMP) (dewatering, fish salvage, turbidity mangement, etc.)
Determine equipment access routes
| Build Design Surface Flow Model (DSFM) @ Baseflow, Q2, Q10, and Q100 | HEC-RAS WORKFLOW
Evaluate Hydrograph from gauge where possible for a given water year
Describe Velocity, Depth, and Inundation
Describe habitat suitability by species and life-stage
| Produce overview maps and PowerPoint of findings | DISCUSSION, DOCUMENTATION, & MAPPING
Refine project goals and objectives with partners
| Develop re-vegetation plan (species, locations, spacing, etc.) | DISCUSSION, DOCUMENTATION, & MAPPING
Develop design logistics and construction needs and sequencing of project elements
Develop Design Packet for Permits
PROJECT IMPLEMENTATION | Implementation and Inspection (Process-Reset)
Public notification and potential area closures
Construction staking (Elevation Hubs, Avoidance Areas, Retention Pools, etc)
Clearing (Access Routes and Cut Surfaces)
Harvest, deliver, and stockpile large wood
Dewatering (construct flow diversion / bypass channel(s), fish salvage, turbidity management, etc.)
Excavate material from cut source areas
Place fill in Incised Channels
Place, bury, and construct large wood structures
Rewater completed surfaces and remove dewatering facilities
Revegetated disturbed areas
Repair permanent access routes, Decommission Staging/stockpile areas and temp access routes
MONITORING | Post-Project Monitoring and Assessment
Establish a monitoring plan to track goals and objectives of the project
Analyze and report on the results of monitoring data
Document lessons learned throughout the project
Share outcomes (presentations, site visits, story maps, publish, etc.)
Note on B19: ====== ID#AAAA_b-j5Zs paul.powers@usda.gov (2023-11-15 17:25:34) The intent of this step is to differentiate between features on the valley floor vs the valley's fluvial process domain. We want to see where landslides, tributary fans, etc impact valley confinement.
Note on B27: ====== ID#AAAA_ckIZoA paul.powers@usda.gov (2023-11-15 17:27:35) The intent of this step is to define the extents of individual valley segments and define the geomorphic control that is responsible for the development of those valley segments.
Note on B32: ====== ID#AAAA_ckIZoE paul.powers@usda.gov (2023-11-15 17:36:27) At this point, we have gained some context about the watershed, connectivity, or lack thereof between valley segments, and the basic underlying elements of the watershed. ------ ID#AAAA_ckIZoI paul.powers@usda.gov (2023-11-15 17:38:03) This should help guide the next steps by providing some relative/weighted extent of given valley segments
Note on B48: ====== ID#AAAA_ckIZoQ paul.powers@usda.gov (2023-11-15 17:48:38) In the previous steps we identified natural or hillslope features impacting the fluvial process space, now we are taking this a step further to identify anthropogenic features (roads, berms, dams...)
Note on B66: ====== ID#AAAA_ckIZoM paul.powers@usda.gov (2023-11-15 17:44:18) This early modeling work allows the team to evaluate the impacts of the current condition and make educated decisions in regards to what restoration scenarios they may want to peruse. For example, this modeling would give a quantifiable difference between current and future conations, but it also allows the team to see the relative tradeoffs of keeping or relocating anthropogenic features on the valley. I.E. if this road/campground were relocated, it might open access to this much additional process space...
Note on C72: ====== ID#AAAA_ckIZoc Brian Cluer - NOAA Federal (2023-11-15 19:20:24) The SEM from Cluer and Thorne 2014, where the concept of Stage 0 originated. Naturally, different settings offer different restoration potential, depending on site history and external drivers. For example, where an alluvial valley is pinched by a tributary fan deposit a single thread channel is the undisturbed form and a Stage 1 configuration is a productive goal. Depending on the degree of incision and other constraints, there is a choice to make about whether to restore to Stage 0 or to accelerate natural widening processes to create Stage 8 conditions.
Note on B73: ====== ID#AAAA_ckIZoU paul.powers@usda.gov (2023-11-15 18:04:26) Underlying this decision are some relatively simple scale elements 1. Does your stream/valley deliver enough sediment (if captured/retained) to accrete the bed and eliminate incision? 2. Can that material be captured, resulting in uplift of the entire valley (not just at a few discrete locations). 3. If yes and yes, how long might that take? Do you have the time to wait for that?
Note on B77: ====== ID#AAAA_ckIZoY paul.powers@usda.gov (2023-11-15 18:08:50) This is a very important step where validation of REM elevation bands occurs. Do we find evidence of pre-degradation flow paths at the GGL target elevation, are we seeing old growth upland species stumps on REM colors that imply a high degree of wetness? If so, adjustment is needed.
Note on C93: ====== ID#AAAA_ckIZog Brian Cluer - NOAA Federal (2023-11-15 19:21:08) With clear project potential and restoration goals established, we consider the most effective approach. There is a spectrum of different intervention pathways to achieve restoration goals that depend on the scale of the problem, the desired time to achieve results, and the social and regulatory landscape. ltPBR (Wheaton et al) is represented on the far left side of the diagram, which I call ‘process-led’, because its aim is to work with physical processes to advance the evolution of an incised stream to a more ecologically productive state, often requiring additional erosion in order to generate a local sediment supply. This approach is led by interventions that harness the power of physical processes. It can be widely applied by mostly manual labor, but it is intended to be temporary and incremental, requiring multiple interventions in most locations. It is unlikely to work in streams that are deeply incised, unless a lot of additional erosion can be tolerated. It can add some functional but temporary complexity to channels in non-alluvial settings, and that is sometimes the extent of the habitat goal. Exhuming valleys that are buried in Anthropocene sediment is on the far right side of the diagram, and this condition is actually common on WCR coastal lowlands. It has been used successfully in the Chesapeake Bay (Merritts et al), but has not been applied at valley scale on the West Coast yet, although Five Mile – Bell is the largest example to date. Valley grading, or the valley reset approach, basically removes unused infrastructure (levees, dikes, old roads, etc.) and fills oversized channels ((Powers et al) by lowering anthropogenically elevated valley deposits. This approach is also represented on the right side, which I call ‘process-reset’, because its aim is to replace the counterproductive erosion and high transport process by eradicating the offending incised (or oversized) channel, and reset the main physical process that created the alluvial valley in the first place = deposition. This, and

## Examples
Detailed examples are still under development.
For now, please see the link for the example below.
Link Example: | https://stagezeroriverrestoration.com/docs/resources/mathias.pdf